## APPROVAL DRAWINGS PROCESS
STEP 1 | The crane project coordinator recieves original copy of drawings from vendor of crane system.
STEP 2 | System drawings are sent to the customer to review. Territory manager and sales representative should be copied in email.
STEP 3 | Did customer issue comments for revisions on the submitted crane system design drawings?
STEP 3A | Revised system drawings are requested and obtained from the vendor per the customers request.
STEP 4 | The drawing is signed and dated for approval by customer and received by Hi-Speed crane project coordinator before proceeding.
STEP 5 | The signed and dated approval drawings are sent to the vendor & territory manager by the crane project coordinator to secure materials and confirm ship date.

## APPROVAL DRAWING FLOWCHART
YES
NO
The crane project coordinator recieves original copy of drawings from vendor of crane system.
System drawings are sent to the customer to review. Territory manager and sales representative should be copied in email.
Did customer issue comments for revisions on the submitted crane system design drawings?
Revised system drawings are requested and obtained from the vendor per the customers request.
The drawing is signed and dated for approval by customer and received by Hi-Speed crane project coordinator before proceeding.
The signed and dated approval drawings are sent to the vendor & territory manager by the crane project coordinator to secure materials and confirm ship date.