## UNRECEIVED
Date of PO Receipt | Po Number | Description of PO | Amount | Method | Cust Number | Cust Name | Customer Master | Order/Job | Branch | Dept assigned | Rec'd in ACS | Promise Date | "BY" | Job Status | Invoice
2019-05-21 | 4501782139 | Fork: RailStop | 310.42 | email | 000312 | Nyrstar | Nyrstar | NA | 1 | NA | N | NA | NA
2019-05-24 | 4501480724 | Repair Remote Transmitter | 1.00 | email | 003814 | Atlas Tube | Atlas Tube | NA | 1 | Hoist Repair | N | NA | NA
2019-06-21 | 4500966097 | Vibration Analysis | 2600.00 | email | 004293 | Arkema |  | NA | 1 | Motor Repair | N | NA | NA
2019-06-28 | 4500146599 | Service/replace rope on job | 8423.72 | email | 000078 | The Bryce Co, LLC | Bryce Corp. Memphis | NA | 1 | Hoist Repair | N | NA | NA
2019-07-03 | 9900863580 | Balance Fan Blower | 0 | email | 000180 | Chemours Company | Chemours Company | NA | 1 | Motor Repair | N | NA | A. SKALA
2019-07-03 | PII-667 | Supply/Install trolley system | 59247.63 | email | 004767 | Big River Steel | Big River Steel | NA | 1 | Hoist Repair | N | NA | NA
2019-07-03 | AR2050016 | Sling RAI | 233.42 | email | 001514 | Sonoco Products | Sonoco Products | NA | 1 | Hoist Repair | N | NA | NA
2019-07-08 | 1941230259 | Repair induction pump/motor | 2180.00 | email | 011685 | Welspun Tubular | Welspun Tubular | NA | 2 | Motor Repair | N | NA | D. JACKSON
2019-07-08 | UORP15475 | Harrington latch kits | 11.12 | email |  | CATERPILLAR | CATERPILLAR | NA | 1 | Inside Sales | N | NA | NA
2019-07-08 | USMMMPYGH9 | Replacement Motors | 0 | email | 10001 | 3M | 3M | NA | 2 | Inside Sales | N | NA | NA

## COMPLETED
# | Date of Receipt of PO | PO Number | Description of PO | Amount | Method of Transmission, Fax, Email, Phone, Other | Customer number | Customer Name | Master Customer | Order/Job/Quote/Estimate | Branch | Department Assigned PO | Received in ACS | Promise Date | "By" | JOB STATUS | INVOICE
13 | 2019-05-02 | 450095823 |  |  | email | 004293 | ARKEMA |  |  |  | Inside | Y | 2019-05-16 | J. PITMAN | OPEN
15 | 2019-05-02 | 4400098327 | Troubleshooting labor, brake assembly, and install labor | 2858.84 | email | 001217 | ABB |  | 139658 | 1 | Hoist Repair | Y | 2019-06-21 | T. SHOOK | COMPLETED | 258289
8 | 2019-05-02 | 113042 | Friction Disc set | 41.75 | email | 004849 | CRW Hawaii |  | 81943 | 1 | Inside | Y | 2019-05-09 | S. SULLIVAN | COMPLETED | 257298
9 | 2019-05-02 | USMMMNGKX9 | Fan, cover, screw, gasket |  | email | 010001 | 3M | 3M Company | 20780 | 2 | Inside Sales | Y | 2019-06-27 | T. THOMPSON | OPEN
11 | 2019-05-02 | I000174542 |  |  | email | 004622 | CAT |  |  |  | Inside | N |  | S. CHADWICK | OPEN
14 | 2019-05-02 | I000174666 | Adder for 2 shifts for 3508 crane installation |  | email | 004622 | CAT |  | 138657 | 1 | Crane | Y | 2019-05-27 | T Shook | COMPLETED | 257851
16 | 2019-05-03 | UOGR05198 | Demag Hoist |  | email | 004622 | CAT |  | 82014 | 1 | Inside Sales | y | 2019-05-10 | J. PTMAN | COMPLETED | 257343
19 | 2019-05-03 | 09681 | Balance Rotor | 1094.01 | email | 012194 | Highland Pellets - Pine Bluff |  | 95525 | 2 | Motor Repair | Y | NA | D. JACKSON | COMPLETED | 56215
20 | 2019-05-03 | 4600224744 | Hoist, Muffler, Controls |  | email | 000134 | Cooper Tire & Rubber |  | 0081974 | 1 | Inside Sales | Y | 2019-05-17 | S. CHADWICK | OPEN
21 | 2019-05-03 | 5002621918 | Pendant Coffing |  | email | 004324 | Airgas |  | 20789 | 2 | Inside Sales | Y | 2019-05-06 | S. CHADWICK | COMPLETED | 56199
| 2019-05-03 | 366839(JAC) | Hoist Repair (RAI) | 2410.46 | email | 004609 | Pinnacle Foods |  | 139723 | 1 | Hoist Repair | Y | 2019-06-07 | E. MARTIN | WIP
| 2019-05-03 | 1941210476 | Transmitter, 10 TON Crane | 470 | email | 11685 | Welspun Tubular |  | 20793 | 2 | Inside Sales | Y | 2019-05-15 | T. THOMPSON | COMPLETED | 56337
23 | 2019-05-05 | 4501777057 | Motor, 1.5HP |  | email | 000312 | Nyrstar | Nyrstar Clarksville, Inc. | 81991 | 1 | Inside Sales | Y | 5/8/2019 | S. CHADWICK | COMPLETED | 257578
25 | 2019-05-05 | 6700002999 | Supply & install power rail |  | email | 004564 | FSBP Prescott | Firestone Diversified | 95543 | 2 | Hoist Repair | Y | 2019-06-06 | D. JACKSON | OPEN
| 2019-05-05 | 9900829877 | Inspect/repair hoist in 450 maint shop | 526.43 | email-submitted by D. Shook | 000180 | Chemours Co. | Chemours Co | 139728 | 1 | Motor Repair | Y | 2019-06-15 | E. MARTIN | OPEN
26 | 2019-05-06 | 1941210497 | Cable 4C |  | email | 004570 | Welspun Tubular | Welspun Tubular | 20806 | 2 | Inside Sales | Y | 2019-05-17 | T. THOMPSON | COMPLETED | 56296
27 | 2019-05-06 | 1941230141 | Repairing motor |  | email | 11685 | Welspun Tubular | Welspun Tubular | 95557 | 2 | Motor Repair | Y | 2019-06-09 | D. JACKSON | OPEN
28 | 2019-05-07 | 4501777585 | Motor 3hp |  | email | 000312 | Nyrstar |  | TBD | 1 | Inside Sales | Y | TBD | S. CHADWICK | OPEN
29 | 2019-05-07 | 4500122575 | Kit-Stearns Disc |  | email | 004564 | Firestone BP |  | 20805 |  | Inside Sales | Y | 2019-05-17 | No one claimed it | OPEN
30 | 2019-05-07 | 1900568N1 | Carbon brushes |  | email | 004841 | Harriman Material |  | 0082049 | 1 | Inside Sales | Y | 2019-05-16 | S. SULLIVAN | OPEN
31 | 2019-05-07 | 0255043 | Parts & labor chilled water pump |  | email | 001255 | University of Memphis |  | 139716 | 1 | Inside Sales | Y | SERVICE TBD | J. PITMAN | OPEN
34 | 2019-05-08 | 196491 | Top Hook, Bottom Hook, Bolt |  | email | 004820 | American Riggers |  | 0082054 | 1 | Inside Sales | Y | NA | J. PITMAN | OPEN
35 | 2019-05-08 | 4502672821 | Annual Crane & Hoist Inspec |  | email | 001217 | ABB |  | 139864 | 1 | Hoist Repair | Y | 2019-05-14 | E. MARTIN | OPEN
33 | 2019-05-08 | RFQ | Galvanized Wire Rope | 14.25 | email | 004841 | Harriman Material |  | 0082049 | 1 | Inside Sales | Y | 2019-05-16 | S. SULLIVAN | OPEN
38 | 2019-05-09 | 10091303 | Inspections 3 cranes |  | email | 004261 | ESCO |  | 139580 | 1 | Hoist Repair | Y | HSC | A. OCONNOR | OPEN
41 | 2019-05-09 | 1941230150 | 49KW Motor repair overhaul | 2180 | email | 004570 | Welspun Tubular |  |  |  | Inside Sales |  |  | D. JACKSON | OPEN
| 2019-05-10 | 4502671798 | Balance Low Pressure Blower | 200 | email | 001659 | Weyerhauser |  | 139689 | 1 | Inside Sales | Yes | NA | J. PITMAN | OPEN
42 | 2019-05-10 | 8502216016 | Mini-puller, 1.2 ton Harrington |  | email | 005311 | Pfizer |  | 0081109 | 1 | Inside Sales | Y |  | J. PITMAN | OPEN
46 | 2019-05-10 | 4700845091 | 3-ton wire rope repl after inspection |  | email | 003306 | Reinhausen |  | 139741 | 1 | Hoist Repair | Y |  | J. PITMAN | OPEN
48 | 2019-05-10 | 54488 | Harr Dual Speed Switch |  | email | 004901 | Hoist Direct |  | 0082115 | 1 | Inside Sales | Y | 2019-05-10 | S. SULLIVAN | COMPLETED | 257320
49 | 2019-05-10 | 8502217178 | Ann Inspection lifting unit & hoist |  | email | 005311 | Pfizer |  | 0081109 | 1 | Inside Sales | Y | 2019-05-31 | J. PITMAN | OPEN
52 | 2019-05-10 | 54494 | Harr plates, bush, pin |  | email | 004901 | Hoist Direct |  | 0082137 | 1 | Inside Sales | Y | 2019-05-21 | S. SULLIVAN | COMPLETED | 257705
54 | 2019-05-10 | 1941210598 | Control station, pendant |  | email | 004570 | Welspun |  | 0020822 | 2 | Inside Sales | Y | 2019-05-15 | T. THOMPSON | OPEN
51 | 2019-05-10 | 4501779154 | wheel:track assembly for crane | 299 | email | 000312 | Nyrstar | Nyrstar Clarksville, Inc | 0082129 | 1 | Inside Sales | Y | 2019-05-20 | S . CHADWICK | COMPLETED | 257579
59 | 2019-05-13 | 10091521 | Load Test Hoist | 702.61 | email | 004261 | ESCO |  | 139763 | 1 | Hoist Repair | Y | 2019-05-17 | E. MARTIN | COMPLETED | 257862
60 | 2019-05-13 | 4400097400 | Jib Crane repair | 1127.75 | email | 001217 | ABB |  | 139451 | 1 | Hoist Repair | Y | 2019-06-26 | E. MARTIN | COMPLETED | 257358
58 | 2019-05-13 | USMMMNMDM6 | Motor 10HP |  | email | 010001 | 3M | 3M Company | 0020823 | 2 | Inside Sales | Y |  | T. THOMPSON | COMPLETED | 56272
57 | 2019-05-13 | USMMMNKCT4 | Motor 7 1/2hp |  | email | 010001 | 3M | 3M Company | 0020824 | 2 | Inside Sales | Y |  | T. THOMPSON | COMPLETED | 56273
63 | 2019-05-14 | 38366 | RP-2-2 pendant, 2 button | 394.4 | email | 001664 | Young Touchstone |  | 0082064 | 1 | Inside Sales | Y | 2019-05-17 | S. CHADWICK | COMPLETED | 257804
63 | 2019-05-14 | UOGR06593 | Demag Hoist Unit | 1362.14 | email | 004622 | Caterpillar |  | 0082139 | 1 | Inside | Y |  | J. PITMAN | COMPLETED | 257573
| 2019-05-14 | 4501479791 | Repair Saw Pump | 1 | email | 003814 | Atlas Tube |  | NA | 1 | Inside Sales | Y | 2019-05-15 | J. PITMAN | OPEN
64 | 2019-05-14 | 4400098639 | Crane Remote Repair |  | email | 001217 | ABB |  | 139740 | 1 | Hoist Repair | Y | 2019-06-17 | E. MARTIN | OPEN
64 | 2019-05-14 | 130053 | Contactor | 355.81 | email | 001463 | Plymouth Tube |  | 0082085 | 1 | Inside Sales | Y | 2019-05-21 | J. PITMAN | COMPLETED | 257592
65 | 2019-05-15 | 8502222366 | Hoist Inspection | 600.88 | email | 005311 | Pfizer |  | 0081109 | 1 | Inside Sales | Y | 2019-05-31 | J. PITMAN | OPEN
67 | 2019-05-15 | 1941210678 | Crane Transmitter | 610.4 | email | 004570 | Welspun |  | 0020854 | 2 | Inside Sales | Y | 2019-05-31 | T. THOMPSON | COMPLETED | 56346
66 | 2019-05-15 | 559414-TBT | Repair 185kw Motor | 11500 | email | 003323 | Toyota Boshoku |  | 139436 | 1 | Motor Repair | Y | 2019-05-31 | A. SKALA | COMPLETED | 257816
68 | 2019-05-16 | 6700003058 | Replace CR1Z Hoist | no amount | email | 010107 | Firestone BP |  | NA | 2 | Inside Sales | N | NA | T. THOMPSON | OPEN
71 | 2019-05-16 | 51-409412 | Controller | 776.27 | email | 000036 | Anel |  | 139667 | 1 | Hoist Repair | Y | 2019-05-02 | E. MARTIN | COMPLETED | 257507
72 | 2019-05-16 | 4501480020 | Controller | 1 | email | 003814 | Atlas Tube |  | 140014 | 1 | Hoist Repair | Y | 2019-06-20 | E. MARTIN | OPEN
73 | 2019-05-16 | 4501480022 | Controller | 1 | email | 003814 | Atlas Tube |  | 140015 | 1 | Hoist Repair | Y | 2019-06-20 | E. MARTIN | OPEN
74 | 2019-05-16 | 4501480027 | Remote; Transmitter | 1 | email | 003814 | Atlas Tube |  | 140013 | 1 | Hoist Repair | Y | 2019-06-20 | E. MARTIN | OPEN
| 2019-05-16 | 4501480019 | Controller | 1 | email | 003814 | Atlas Tube |  | 139802 | 1 | Hoist Repair | Y | 2019-06-24 | E. MARTIN | OPEN
69 | 2019-05-16 | 4500123299 | Cable/3ton crane, Yale | 5957.6 | email | 10107 | FSBP Prescott | Firestone Diversified | 0020837 | 2 | Inside Sales | Y | 2019-05-23 | J. PITMAN | OPEN
75 | 2019-05-17 | 4501480073 | Repair remote transmitter | 2 | email | 003814 | Atlas Tube |  | 140012 | 1 | Hoist Repair | Y | 2019-06-20 | E. MARTIN | OPEN
76 | 2019-05-17 | 50-P81578 | Rope,wire & ferrule assembly | 455.43 | email | 004463 | IBT |  | 0020808 | 1 | Inside Sales | Y | 2019-05-17 | J. PITMAN | COMPLETED | 56275
| 2019-05-17 | AR2033494 | April Sling Inspection | 266.74 | email | 001514 | Sonoco |  | 139777 | 1 | Hoist Repair | Y | 2019-05-20 | E. MARTIN | COMPLETED | 257470
| 2019-05-17 | AR2033492 | 2019 Annual Inspection | 680 | email | 001514 | Sonoco |  | 139778 | 1 | Hoist Repair | Y | 2019-05-20 | E. MARTIN | COMPLETED | 257471
| 2019-05-17 | SVC1233 | Annual Inspection | no amount | email | 011426 | ITW Shippers Products |  | 95601 | 2 | Hoist Repair | Y | 2019-06-22 | D. JACKSON | COMPLETED | 56520
| 2019-05-17 | 1181102198 | AMT motor/pump 3" in/out | 1355 | email | 012181 | Waste Management |  | 20819 | 2 | Inside Sales | Y | 2019-05-16 | T. THOMPSON | COMPLETED | 56240
| 2019-05-17 | 1941230158 | Repair 50hp motor | 5400 | email | 011685 | Welspun |  | 95562 | 2 | Motor Repair | Y | 2019-07-12 | D. JACKSON | COMPLETED | 56361
| 2019-05-17 | 270520251TRF | Motor Repair | 47820 | email | 011864 | Alcoa Remediation |  | 95350 | 2 | Motor Repair | Y | NA | D. JACKSON | COMPLETED | 56214
| 2019-05-20 | 4500123536 | Brake Motor Hub Yale | 965.44 | email | 004564 | FSBP Prescott | Fireston Diversified | 0020853 | 2 | Inside Sales | Y | 2019-06-07 | J. PITMAN | COMPLETED | 56574
| 2019-05-20 | 4500960822 | Vibration Analysis | 1200 | email | 004293 | Arkema |  | 139769 | 1 | Motor Repair | Y | NA | D. SHOOK | COMPLETED | 255589
| 2019-05-21 | 670003105 | Shutdown Sir E-bar/lifts | 28288.62 | email | 04564 | Firestone BP |  | NA | 2 | Hoist Repair | N | NA | D.JACKSON | OPEN
| 2019-05-21 | 10084682 | Ovehead Crane Rail | 28476.87 | email | 004261 | ESCO |  | NA | 1 | Hoist Repair | N | NA | NA | OPEN
| 2019-05-21 | 51409435 | Service call Deshazo Crane | 514.02 | email | 000036 | Anel |  | 139685 | 1 | Hoist Repair | Y | 2019-05-19 | E. MARTIN | COMPLETED | 257558
18 | 2019-05-21 | 4501822547 | 75HP 1200RPM | 4700 | email | 003468 | Kruger |  | 82289 | 1 | Inside Sales | Y | NA | S. CHADWICK | COMPLETED | 257789
| 2019-05-21 | 4501782013 | Fork Rail | 310.42 | email | 000312 | Nyrstar |  | 0082227 | 1 | Inside Sales | Y | 2019-05-30 | S. CHADWICK | COMPLETED | 257802
| 2019-05-21 | 5894811 | Limit Switch Assembly | 134.55 | email | 002960 | MSC |  | 0082324 | 1 | Inside Sales | Y | 2019-06-07 | J. PITMAN | COMPLETED | 257899
| 2019-05-21 | 50-P82728 | Routing Guide | 1081.5 | email | 011677 | IBT |  | 0020863 | 2 | Inside Sales | Y | 2019-07-12 | S. CHADWICK | COMPLETED | 56429
| 2019-05-21 | 29532954 | Annual Crane Inspection | 2075 | email | 001803 | Berry Plastics | Berry Plastics | 139746 | 1 | Hoist Repair | Y | 2019-05-21 | E. MARTIN | WIP
| 2019-05-22 | 1841230925 | Svc for Induction recooler motor | 2480.84 | email | 011685 | Welspun Tubular |  | 95430 | 2 | Motor Repair | Y | 2019-06-22 | D. JACKSON | WIP
| 2019-05-21 | I000187504 | 1200-4090 10MM | 767 | email | 11795 | Caterpillar |  | 20858 | 2 | Inside Sales | Y | 2019-05-23 | T. THOMPSON | COMPLETED | 56298
| 2019-05-22 | 1841230758 | Motor overhauling | 1435.54 | email | 011685 | Welspun |  | 56356 | 2 | Motor Repair | Y | 2019-05-31 | T. THOMPSON | COMPLETED | 56356
| 2019-05-22 | 1941230148 | Hot Well Pump Motor | 5995 | email | 011685 | Welspun |  | 20867 | 2 | Motor Repair | Y | NA | T. THOMPSON | COMPLETED | 56331
| 2019-05-22 | 416154 | Crane Inspection | 761.46 | email | 005038 | Kasai NA |  | 139861 | 1 | Hoist Repair | Y | 2019-06-01 | E. MARTIN | COMPLETED | 257913
| 2019-05-22 | 05-5340E | Two Speed Button Switch | 316 | email | 004032 | Electrical Automation |  | 82143 | 1 | Inside Sales | Y | 2019-05-28 | S. CHADWICK | COMPLETED | 257790
| 2019-05-23 | 6700003121 | Repair Sir Crane Rails | 15000.00 | email | 004564 | FSBP Prescott | Firestone Diversified | 95571 | 2 | Hoist Repair | Y | 2019-06-15 | D. JACKSON | WIP
| 2019-05-23 | 4500125077 | Kit Stearns Disc | 852 | email | 010107 | Firestone BP | Firestone Diversified | 20877 | 2 | Inside Sales | Y | NA | J. PITMAN | COMPLETED | 56366
65 | 2019-05-23 | 1575257 | Regen Blower | 2010 | email | 004689 | MicroPort |  | 004689 | 1 | Inside Sales | Y | NA | S. CHADWICK | COMPLETED | 257788
| 2019-05-28 | 38452 | Contactor, 10 button enclosure | 469.49 | email | 001664 | Young Touchstone |  | 82239 | 1 | Inside Sales | Y | NA | S. CHADWICK | COMPLETED | 257876
| 2019-05-28 | 38443 | Repair on 5 ton Shawbox | 4424.25 | email | 001664 | Young Touchstone | Young Touchstone | 139800 | 1 | Hoist Repair | Y | 2019-06-19 | E. MARTIN | WIP
| 2019-05-28 | 55431 | Safety latch assy, hook | 630 | email | 005170 | Am Crane & Equipment | Am Crane & Equipment | 82434 | 1 | Inside Sales | Y | 2019-05-28 | S. SULLIVAN | COMPLETED | 257704
| 2019-05-29 | 4501481019 | Repair remote transmitter | 250 | email | 003814 | Atlas Tube | Atlas Tube | 139880 | 1 | Hoist Repair | Y | 2019-06-24 | E. MARTIN | OPEN
| 2019-05-30 | 311811544 | Vibration Analysis | 1295 | email | 004524 | Lanxess | Lanxess | 139853 | 1 | Motor Repair | Y | 2019-05-31 | D. SHOOK | OPEN
| 2019-05-30 | 4400174114 | Dry Ice Mesnac Eq | 8038 | email | 000134 | Cooper Tire |  | 139554 | 1 | Motor Repair | Y | NA | A. SKALA | COMPLETED | 257763
| 2019-06-03 | 38484 | Complete motor assembly | 1812.17 | email | 001664 | Young Touchstone |  | 82640 | 1 | Inside Sales | Y | 2019-06-07 | S. CHADWICK | COMPLETED | 257876
| 2019-06-04 | 10092782 | Insp building structure | 36085.86 | email | 004261 | ESCO |  | 139763 | 1 | Hoist Repair | Y | 2019-05-17 | E. MARTIN | COMPLETED | 257862
| 2019-06-04 | 10092782 | Load Test/Hoist rebuild | 82636.29 | email | 004261 | ESCO |  | 139759 | 1 | Hoist Repair | Y | 2019-05-31 | E. MARTIN | COMPLETED | 257861
| 2019-06-05 | 4500904643 | Trolley/Tool Balancer | 216.4 | email | 010603 | Lanxess/Great Lakes | CHEMTURA | 20928 | 2 | Inside Sales | Y | 2019-06-12 | T. THOMPSON | COMPLETED | 56452
| 2019-06-06 | FRD11422 | Balance E Air Fan | 464 | email | 001441 | Lucite |  | 139881 | 1 | Motor Repair | Y | NA | KW MAXWELL | COMPLETED | 258368
| 2019-06-06 | 4500739187 | 2ply 4" Web Sling | 334.74 | email | 000457 | Solae, LLC | Solae, LLC | 82570 | 1 | Inside Sales | y | 2019-06-17 | J. PITMAN | OPEN
| 2019-06-07 | 4400174975 | 1/2 T Hoist ER2005 | 3349.75 | email | 000134 | Cooper Tire | Cooper Tire | 82592 | 1 | Inside Sales | Y | NA | J. PITMAN | COMPLETED | 257970
| 2019-06-10 | 10093081 | Load test 2 cranes | 3028.38 | email | 004261 | ESCO | ESCO | 138997 | 1 | Hoist Repair | y | 2019-06-30 | E. MARTIN | COMPLETED | 257940
| 2019-06-10 | 38549 | Annual Hoist Inspection | 3500 | email | 001664 | Young Touchstone |  | 139981 | 1 | Hoist Repair | Y | 2019-07-01 | E. MARTIN | COMPLETED | 258021
| 2019-06-10 | 196898 | 5 Ton Latch Key Assy | 26.55 | email | 005158 | American Riggers | American Riggers Supply | 82632 | 1 | Inside Sales | Y | NA | S. SULLIVAN | COMPLETED | 257959
| 2019-06-11 | 4400175157 | Annual Hoist Inspection | 14800 | email | 000134 | Cooper Tire |  | 139950 | 1 | Hoist Repair | Y | 2019-06-29 | G. FAULKNER | OPEN
| 2019-06-12 | 165092 | 1 Ton Hoist | 6852.62 | email | 000188 | ERMCO | ERMCO | 82609 | 1 | Inside Sales | Y | 2019-06-24 | J. PITMAN | COMPLETED | 258230
| 2019-06-12 | 4507874298 | Check Pendant on 1/2 Ton | 668.56 | email | 004169 | Siemens Industries | Siemens Industries | 139484 | 1 | Hoist Repair | Y | 2019-06-25 | E. MARTIN | COMPLETED | 258071
| 2019-06-13 | 311820254 | Install 2 Work Station Hoist | 27059.00 | email | 010603 | Rhein Chemie | Lanxess | 139964, 139965 | 2 | Hoist Repair | Y | NA | T. SHOOK | OPEN
| 2019-06-17 | 200470 | Crane PB Station | 403.78 | fax | 000571 | Packaging Corp | Packaging Corp of Am | 82755 | 1 | Inside Sales | Y | 2019-07-01 | J. PITMAN | OPEN
| 2019-06-18 | S0466 | Hook Mount Elec Hoist | 3750 | email | 004192 | Blues City Brewery | Blues City Brewery, LLC |  | 1 | Inside Sales | y | 2019-06-28 | S. CHADWICK | OPEN
| 2019-06-18 | 197023 | Top/Bottom Hook Assy, latch kit | 630.42 | email | 005158 | Herzog | American Riggers | 82762 | 1 | Inside Sales | Y | 2019-06-27 | S. SULLIVAN | COMPLETED | 258339
| 2019-06-19 | 10238 | Balance line 4 Fan | 1500 | email | 012194 | Highland Pelletts |  | 95685 | 2 | Inside Sales | Y | 2019-06-24 | D. WiLLIAMS | COMPLETED | 56468
| 2019-06-20 | 51071741 | parts & labor 50 T Crane | 24723 | email | 002693 | Marathon Equipment |  | 138356 | 1 | Hoist Repair | Y | 2019-06-26 | E. MARTIN | COMPLETED | 258154
| 2019-06-20 | 54952 | Latch kit, screws, springs, | 67.73 | email | 004901 | Hoist Direct |  | 82840 | 1 | Inside Sales | Y | 2019-07-11 | J. PITMAN | OPEN
| 2019-06-20 | W6306 | Trolley idler wheel/geared assy | 311.08 | email | 004822 | Shannahan Crane |  | 82793 | 1 | Inside Sales | Y | 2019-06-24 | G. SASSCER | COMPLETED | 258162
| 2019-06-20 | 55748 | 2 spd pendant, 2spd hoist | 0 | email | 005170 | American Crane |  | 82821 | 1 | Inside Sales | Y | 2019-07-15 | J. PITMAN | OPEN
| 2019-06-21 | 5354000 | Repair conductor bar SCC Unit 1 | 12657.56 | email | 003518 | TVA Southaven |  | 140010 | 1 | Hoist Repair | Y | 2019-06-19 | G. FAULKNER | COMPLETED | 258348
| 2019-06-21 | 19-00742E-1 | Wire rope | 710.74 | email | 004841 | Taghleef Industries | Harriman Material | 82833 | 1 | Inside Sales | Y | 2019-07-05 | S. CHADWICK | OPEN
| 2019-06-21 | 4501791271 | Gearbox:Crane dual motor #2 | 5061.91 | email | 000312 | Nyrstar | Nyrstar Clarksville, Inc | 139919 | 1 | Motor Repair | Y | NA | A. SKALA | OPEN
| 2019-06-24 | F006234 | On/Off Switch | 250 | email | 010636 | Gerdau | Gerdau | 20993 | 2 | Inside Sales | Y | 2019-06-24 | J. PITMAN | OPEN
| 2019-06-24 | 4500127698 | Yale Relays | 140.9 | email | 010107 | FSBP Prescott | Firestone Diversified | 20995 | 2 | Inside Sales | Y | 2019-07-12 | J. PITMAN | OPEN
| 2019-06-24 | 13381304 | Remote charger/battery kit | 523.49 | email | 003292 | International Paper | International Paper | 82184 | 1 | Inside Sales | Y | 2019-06-28 | S. CHADWICK | OPEN
| 2019-06-24 | Y4098480 | (2) Trolleys ETRK 2ET2600-4 | 1707.58 | email | 000525 | S. Cotton Oil | Archer Daniels Midland | 82844 | 1 | Inside Sales | Y | 2-3 weeks | S. CHADWICK | OPEN
| 2019-06-24 | 200604 | PB-3A | 92.00 | fax | 000571 | Packaging Corp of AM | Packaging Corp of Am | 83017 | 1 | Inside Sales | Y | NA | J. PITMAN | OPEN
| 2019-06-24 | 10258 | Balance Dry Hammermill Rotor | 2600.00 | email | 012194 | Highland Pellets | Highland Pellets LLC | 95700 | 2 | Motor Repair | Y | 2019-06-30 | D. JACKSON | OPEN
| 2019-06-24 | REPAIR-455 | Submersible Pump Repair | 1.00 | email | 004767 | Big River Steel | Big River Steel | 140050 | 1 | Motor Repair | Y | 2019-06-28 | A. SKALA | OPEN
| 2019-06-24 | 6700003316 | Blanket PO 2019 crane repair | 33600.00 | email | 010107 | FSBP Prescott | Bridgestone Am | NA | 2 | Hoist Repair | N | NA | D. JACKSON | OPEN
| 2019-06-25 | 122159 | Adjust Trolley Speeds | 377.43 | email | 003901 | Plaskolite, Inc. | Plaskolite | 139815 | 1 | Hoist Repair | Y | NA | E. MARTIN | OPEN
| 2019-06-25 | 4507900979 | Install Magnetek Flex Remote | 1847.06 | email | 004169 | Siemens | Siemens | 140049 | 1 | Hoist Repair | Y | 2019-07-05 | E. MARTIN | OPEN
| 2019-06-25 | 1941230196 | Service cooling tower pump | 1000.00 | email | 011685 | Welspun Tubular | Welspun Tubular | 95610 | 2 | Hoist Repair | Y | 2019-06-24 | D. JACKSON | Open
| 2019-06-26 | S0554 | Quarterly Hoist Inspection | 1680 | email | 004192 | Blues City Brewery | Blues City Brewery | 140070 | 1 | Hoist Repair | Y | 2019-07-15 | E. MARTIN | OPEN
| 2019-06-26 | 4400176551 | Dry Ice for Blaster/clean festoon | 14577.72 | email | 000134 | Cooper Tire | Cooper Tire & Rubber | 140082 | 1 | Motor Repair | Y | 2019-07-05 | A. SKALA | OPEN
| 2019-06-26 | 4500126635 | (3) Harrington 3 Ton Hoist | 30,348.00 | email | 010107 | Firestone Prescott | Bridgestone Am | 20884 | 2 | Inside Sales | Y | 2019-08-01 | T. THOMPSON | OPEN
| 2019-06-26 | 4502710672 | Crane Remote Labels | 320.88 | email | 001217 | ABB, Inc | ABB, Inc | 140066 | 1 | Hoist Repair | Y | 2019-07-05 | LWH | Open
| 2019-06-27 | 38674 | Service call install brake | 3111.35 | email | 1664 | Young Touchstone | Young Touchstone | 139913 | 1 | Hoist Repair | Y | 2019-06-07 | E. MARTIN | OPEN
| 2019-06-28 | 4400176779 | 3 ton battery lift beam | 902.62 | email | 000134 | Cooper Tire | Cooper Tire | 82938 | 1 | Inside Sales | Y | 2019-07-12 | J. PITMAN | OPEN
| 2019-06-28 | CO502718 | Annual Hoist Inspection | 2950.00 | email | 000059 | Baxter Healthcare | Baxter Healthcare | NA | 1 | Hoist Repair | N | NA | E. MARTIN | OPEN
| 2019-06-28 | 4400176779 | E ton hook | 227.97 | email | 000134 | Cooper Tire | Cooper Tire | 82931 | 1 | Inside Sales | Y | 2019-06-29 | J. PITMAN | COMPLETED | 258341
| 2019-06-28 | 4400176878 | Gorbel Bridge kit 500 lb | 4053.00 | email | 000134 | Cooper Tire | Cooper Tire & Rubber | 140085 | 1 | Hoist Repair | Y | 2019-08-01 | T. SHOOK | OPEN
| 2019-06-28 | 4400176878 | Gorbell Bridge Kit 500 lb inst/cert | 5369.31 | email | 000134 | Cooper Tire | Cooper Tire & Rubber | 140086 | 1 | Hoist Repair | Y | 2019-08-01 | T. SHOOK | OPEN
| 2019-06-28 | 40-M246424 | Braking unit | 1915.00 | email | 3974 | Nucor Steel Memphis | Nucor Steel Memphis | 83055 | 1 | Inside Sales | Y | 2019-07-15 | J. PITMAN | OPEN
| 2019-07-01 | 4059368 | Repair P&H 2hp motor | 4395.24 | email | 000418 | Nucor Yamato | Nucor Yamato Steel | 139972 | 1 | Motor Repair | Y | NA | A. SKALA | OPEN
| 2019-07-01 | AR2048406 |  | 1830.15 | email | 001514 | Sonoco | Sonoco-Corp | job | 1 | Hoist Repair | N | NA | E. MARTIN | OPEN
| 2019-07-02 | L1796225 | Inspection | 875.00 | email | 003446 | Columbus McKinnon | Columbus McKinnon | NA | 1 | Hoist Repair | N | NA | E. Martin | OPEN
| 2019-07-02 | 4502716446 | Warning light package | 1668.20 | email | 001217 | ABB, Inc | ABB, Inc | NA | 1 | Hoist Repair | N | NA | W. Hubbard | OPEN
| 2019-07-01 | 1941230316 | motor repair/slitter | 872.00 | email | 011685 | Welspun Tubular | Welspun Tubular | 95610 | 2 | Motor Repair | Y | 2019-06-24 | D. Jackson | OPEN
| 2019-07-02 | 51073626 | SEW gear Motor | 1085.00 | email | 002693 | Marathon Equip. | Marathon Equip | 83022 | 1 | Inside Sales | Y | 2019-07-08 | S. CHADWICK | OPEN
| 2019-07-02 | 2267963 | Motor repair | 67297.05 | email | 000730 | USG Interiors | USG Interiors | 139996 | 1 | Motor Repair | Y | 2019-08-15 | A. SKALA | OPEN
| 2019-07-03 | 0177634 | Limit Switch | 170.61 | email | 004830 | All Lift Systems | All Lift Systems | 83059 | 1 | Inside Sales | Y | 2019-07-03 | S. SULLIVAN | OPEN
| 2019-07-03 | P187097067 | Chain hoist, 2 btn pendant | 2634.00 | email | 11497 | Georgia Pacific/Gurdon | Georgia Pacific/Gurdon | NA | 2 | Inside Sales | N | NA | T. Thompson | OPEN
| 2019-07-03 | P04688712 | Gorbel station and installation | 57060 | email | 1392 | Polyone Corp Dyersburg | Polyone Corp Dyersburg | 140124 | 1 | Hoist Repair | Y | 2019-09-01 | T. SHOOK | OPEN
| 2019-07-08 | 4502716078 | Inspection of 4 hook devices | 941.39 | email | 001217 | Senatobia Plant Assy | ABB, Inc. | NA | 1 | Hoist Repair | N | NA | E. MARTIN | OPEN
| 2019-07-08 | I000219205 | Install buzzer on 6 ton crane | 1368.55 | email |  | CAT | CAT | NA | 1 | Hoist Repair | N | NA | T. SHOOK | OPEN

## Daily Tracker tab
TRACKER | 2019-06-24 | 2019-06-25 | 2019-06-26 | 2019-06-27 | 2019-06-28 | 2019-07-01 | 2019-07-02 | 2019-07-03 | 2019-07-05
Incoming PO #
Incoming PO $
PO# Unreceived
PO$ Unreceived

## RFQ
# | Date of Receipt of PO | PO Number | Description of PO | Amount | Method of Transmission, Fax, Email, Phone, Other | Customer number | Customer Name | Order/Job # this should be our job number or order number | Branch | Department Assigned PO | Received in ACS | Promise Date | "By"
| 2019-06-18 | NG-M389-4R242 | 3 Shackles (gov contract) | no amount | fax |  | JGILS, LLC | [5 empty] | S. SULLIVAN
| 2019-06-20 | IN190619-V4120 | 20 End Link Chain | no amount | email |  | JGILS, LLC |  | 1 | IS